DROP AS BOTH A WORD AND A PDF

Meeting Notes, Project:  Book Transcription; Chart/Table Creation prior to 3/11 Class

| Meeting Number: 1 | Meeting Date: 3/9/2026 | Start Time: 7:00pm | End Time: 8:00pm |
| --- | --- | --- | --- |

| Attendee Name (Indicate note taker with *) | Timeliness (on time, late, left early, missing) |
| --- | --- |
| Ben Lyons* | On time |
| Sean Balbale | On time |
| Zoe Kuehne | On time |
| Aleksandra Postolov | On time |

Purpose:

- Brainstorm plan for how to transcribe book

- Create charts to show workflow of the transcription process (i.e. who does what, when something will happen, etc.)

Agenda:

- Identify tasks

- Identify obstacles

- Assign tasks

- Create charts and tables

Major Accomplishments:

- Created a lucid chart for PERT chart, containing tasks and what could go wrong at each step

- Created the tool selection document with 4 strong options

- Created tables for Task and Roadblock, Task Time, and Task Relationship

Next Steps:

- Make the PERT and Gantt charts

- Transcribe the book according to our plans

Meeting Notes:

Meeting begins at 7:00 pm on Google Meet. Identified tasks. First I went to library. Alecksandra works in library, so could quickly find book. For what could go wrong, various elements such as bad weather, misplaced book, etc.

Added these tasks and the various obstacles that we may encounter into a document as our Lucid Chart. Created a Task/Roadblock table with tasks and possible setbacks with the corresponding optimistic, most likely, and expected times. Made a task dependency table describing what tasks can start when (i.e. what tasks can be done when). Created tool analysis at the top of the document explaining Lucidchart, TeamGantt, Draw.io, and Microsoft Project as viable options for chart creation.

Optimized efficiency of tasks by discussing means such as splitting up paragraphs, proofreading paragraphs as the typers type, and how many people to have transcribing/typing the book.

Documents: (included or links to them)

https://docs.google.com/document/d/1itDQCTzq1UWpo7KJ_9HFh-8OCqYZleZ9dlwnPVJYBRw/edit?tab=t.0