Tool Analysis

- Lucidchart: While the free tier offers a capable node-based canvas for flowcharts and PERT diagrams, the Gantt functionality is limited. The platform requires manual formatting for timelines and lacks automatic calculation for task dependencies.

- TeamGantt: This specialized tool features a drag-and-drop interface that automates duration and overlap calculations. However, it does not support the custom node-based architecture required for PERT charts.

- Draw.io (diagrams.net): Although it is an open-source, cost-effective solution for custom PERT node shapes, it offers no timeline automation, making Gantt chart creation a purely manual and inefficient process.

- Microsoft Project: As the industry standard, it handles both PERT and Gantt generation concurrently. However, the licensing costs and steep learning curve make it impractical for this project.

Selection & Justification

The group opted to use Lucidchart for the PERT chart and TeamGantt for the Gantt chart.

We selected Lucidchart for the PERT requirements because its interface allows us to instantiate custom node shapes to display specific variables, task name, expected time, Earliest/Latest Start and Finish times, and slack time, without a paywall.

For the Gantt chart, we chose TeamGantt to prioritize efficiency. Rather than manually drawing bars in a general diagramming application, TeamGantt’s dedicated engine allows us to visualize start times, task durations, and resource allocation. This approach bridges the gap between high-level planning and precise execution while staying within the project’s free software requirement.

Task Time & Roadblock Table

Tasks-

- Initial Setup (Getting book number and other info)

  - Unclear instructions

- Going to the library-  best case scenario: 3 mins, worst case: 10 mins (Aleksandra, Zoe)

  - Falling (injury)

  - Snow (bad weather)

- Go to the MECC Printer

  - The keycard doesn’t work

  - The printer is out of paper

  - No more printing dollars

- Finding the book-

- The book is lost/missing/displaced

- Forgotten call name

- Travel back to MEC: 3 mins, worst case: 10 mins (Aleksandra, Zoe)

  - Fall

- Transcribing the book

  - Backwards transcription is improperly understood

  - The pages are missing

- Proofread

  - Major error found.

- Printing the transcription

  - Printer jam

- Email Transcription

  - Wifi Drops out

- Hand Deliver to Professor

  - Dr. S stepped out of the classroom

The Expected Time calculation uses the formula: (Optimistic + (4 * Most Likely) + Pessimistic) / 6.

| Task | Setbacks | Resolution Options | Add Time | Optimistic | Pessimistic | Most Likely | Expected |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A. Initial Setup | Unclear Instruction | Clarify with the Professor | +2 min | 2 min | 4 min | 3 min | 3 min |
| B. Going to the Library | Falling (injury) Snow (bad weather) | If a health center is needed, alert the team. Take indoor paths. | +10 min +5 min | 3 mins | 18 | 4 min | 6 mins |
| C. Finding the book | The book is lost/missing/displaced The pages are missing | Try to find a library attendant Contact dr S | 15 3 | 3 | 21 | 4 | 7 min |
| D. Travel back to the MECC | Falling (injury) Snow (bad weather) | If a health center is needed, alert the team. Take indoor paths. | +10 min +3 min | 5 | 18 | 4 | 7 min |
| E. Transcribing the book | Backwards transcription is improperly understood The pages are missing | Teammates will recover the paragraph Contact dr S | +7 mins +10 mins | 10 | 27 | 15 | 16 min |
| F. Travel to MECC printer | Falling Unable to get in the door/No ID access | Send another team member and call for help Try basement printer if no keycard access then LSC | +5 +3 mins +10 mins | 1 min | 19 mins | 4 mins | 6 mins |
| G. Email Transcription | Wifi Drops out MFA doesn’t send authentication token so can’t log into email | Use phone hotspot Another teammate will take over | +1 min +4 mins | 2 mins | 7 min | 4 min | 4 min |
| H. Printing | Printer jam The keycard doesn’t work The printer is out of paper The printer doesn’t have toner | Fix jam Go to LSC printer Go to the basement printer Go to the basement printer | +2 min +4 min +2 min +2 min | +1 min | +11 min | 3 min | 4 min |
| I. Proofreading | Major error found. | Split up the paragraph into the # of teammates able to type and work together | +3 mins | 3 mins | 6 mins | 4 mins | 4 min |
| J. Hand Deliver | Dr. S stepped out of room | Check her office and send an email | +2 min | 4 mins | 6 mins | 5 min | 5 mins |

| Task Name | Expected Time | Predecessors |
| --- | --- | --- |
| A. Initial Setup | 3 mins | None |
| B. Going to the Library | 6 mins | A |
| C. Finding the book | 7 mins | B |
| D. Travel back to the MECC | 7 mins | C |
| E. Transcribing the book | 16 mins | C |
| F. Travel to the MECC printer | 6 min | None |
| G. Printing | 4 min | F,I |
| H. Email Transcription | 4 min | I |
| I. Proofreading | 4 mins | E |
| J. Hand Deliver to Dr. S | 5 mins | G,H |